## Sheet1
Sprint 1
Status | Task id | Task description | Task priority | Task dependency level | Expected duration | Team members in charge | Dependencies
not started | 0 | Create wireframes of the website | High priority | Level 0 | 4 hours | Matthew Brougham and Oli Prajwolshree
not started | 1 | Write HTML and CSS of booking process | High priority | Level 1 | 2 hours | TBC | Task 0
not started | 2 | Write HTML and CSS of login and sign up system | High priority | Level 1 | 2 hours | TBC | Task 0
not started | 3 | Code server file to load current pages | High priority | Level 2 | 20 minutes | TBC | Tasks 0, 1, 2
not started | 4 | Create users database | High priority | Level 0 | 1 hour | Percy Lackgren and Laura McKell
not started | 5 | Create rooms database | High priority | Level 0 | 1 hour | Percy Lackgren
not started | 6 | Create bookings database | High priority | Level 1 | 1 hour | Percy Lackgren | Tasks 4, 5
not started | 7 | Code server file to save and retreive users' account information from database | High priority | Level 3 | 1 hour and a half | Percy Lackgren and Laura McKell | Tasks 0, 1, 2, 4
not started | 8 | Code server file to save and retrieve room availability from database | High priority | Level 2 | 40 minutes | Jon A. Beroz and Percy Lackgren | Tasks 0, 1, 7
not started | 9 | Code javascript of booking process | High priority | Level 4 | 3 hours | Jon A. Beroz | Tasks 0, 1, 2, 3, 4, 5, 6, 7, 8,10
not started | 10 | Code javascript of login and sign up system | High priority | Level 3 | 2 hours | Jon A. Beroz | Tasks 0, 2, 3, 4 , 7
not started | 11 | Write HTML and CCS of page that manages a user's bookings | Medium priority | Level 1 | 30 minutes | Allegra Santoro | Task 0
not started | 12 | Load bookings filtered by user from database and add them to page that manages a user's bookings | Medium priority | Level 4 | 40 minutes | Allegra Santoro | Tasks 0, 1, 2, 3, 4, 6, 7, 9, 10, 11
not started | 13 | Creating cancelling bookings system | Medium priority | Level 5 | 20 minutes | Allegra Santoro | Tasks 0, 1, 2, 3, 4, 6, 7, 9, 10, 11, 12
not started | 14 | Create outlook calendar for every room | Medium priority | Level 0 | 20 minutes | TBC
not started | 15 | Connect the calendar to the booking system | Medium priority | Level 6 | 3 hours | TBC | Task 0, 1, 2, 3, 4, 5, 6 , 7, 8, 9, 10, 11, 12, 13, 14, 19
not started | 16 | Write HTML and CSS of calendar page | Medium priority | Level 1 | 1 hour | TBC | Task 0
not started | 17 | Integrate calendar into calendar page | Medium priority | Level 7 | 30 minutes | TBC | Task 0, 1, 2, 3, 4, 5, 6 , 7, 8, 9, 10, 11, 12, 13, 14, 15, 16
not started | 18 | Write HTML and CSS of booking requests page | Medium priority | Level 1 | 20 minutes | TBC | Task 1
not started | 19 | Load bookings by request status from database | Medium priority | Level 5 | 30 minutes | TBC | Task 0, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
not started | 20 | Integrate system to approve or deny booking | Medium priority | Level 6 | 1 hour | TBC | Task 0, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 19, 20
not started | 21 | Write HTML and CSS of admin page containing all confirmed user bookings | Medium priority | Level 1 | 1 hour | TBC | Task 0
not started | 22 | Code admin cancellation and edit of booking | Medium priority | Level 7 | 1 hour | TBC | Tasks 0, 1, 2, 3, 4, 5, 6, 7, 8, 9,10, 19, 20, 21
not started | 23 | Creating confirmation and notification emails system | Low priority | Level 8 | 2 hours | TBC | Tasks 0, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 19, 20, 21, 22
not started | 24 | Add security measures system | Low priority | Level 4 | 6+ hours | Laura McKell | Tasks 0, 2, 3, 4 , 7, 10
Sprint 2 Part 1
Status | Task id | Task description | Task priority | Task dependency level | Expected duration | Team members in charge | Dependencies
not started | 25 | Create HTML and CSS of page showing booking statistics to admin | Low Priority | Level 0 | 1 hour | TBC
not started | 26 | Code javascript of page showing booking statistics to admin | Low Priority | Level 1 | 4 hours | TBC | Task 25
not started | 27 | Create system that allows users to edit their bookings (+ admin confirmation) | Low Priority | Level 0 | 2 hours | TBC
not started | 28 | Create system to reset account password | Low Priority | Level 0 | 1 hour and a half | TBC
not started | 29 | Create page/system that allows admins to specify why a booking was denied | Low Priority | Level 0 | 30 minutes | TBC
not started | 30 | Create HTML and CSS of page that allows admins to create rooms | Low Priority | Level 0 | 30 minutes | TBC
not started | 31 | Code page to allow admins to create rooms | Low Priority | Level 1 | 1 hour | TBC | Task 30
not started | 32 | Continue implementing security measures | Low Priority | Level 0 | 6+ hours | Laura McKell
Sprint 2 Part 2
Status | Task id | Task description | Task priority | Task dependency level | Expected duration | Team members in charge | Dependencies
not started | 33 | Create system to allow reoccuring bookings | Low Priority | Level 0 | 40 minutes | TBC
not started | 34 | Create program to allow the option to receive email/text alerts on the day of the booking | Minimum priority | Level 0 | 6+ hours | TBC
not started | 35 | Take pictures of the rooms and edit them | Minimum priority | Level 0 | 2 hours | Oli Prajwolshree
not started | 36 | Display images of the rooms | Minimum priority | Level 1 | 10 minutes | Oli Prajwolshree | Task 35
not started | 37 | Create diagrams showing room's availability | Minimum priority | Level 0 | 4 hours | Matthew Brougham
not started | 38 | Create system to allow users to book a specific desk or work station | Minimum priority | Level 0 | 4 hours | TBC
not started | 39 | Create system to allow users to book for others | Minimum priority | Level 0 | 10 minutes | TBC
Sprint 3
Status | Task id | Task description | Task priority | Task dependency level | Expected duration | Team members in charge | Dependencies
not started | 40 | Create guidance document | Minimum priority | Level 0 | 3 hours | TBC
not started | 41 | Refine and test | N/A | Level 0 | Until end of sprint | All