## Sheet1
Status | Task id | Task description | Task priority | Expected duration | Team members in charge
finished | 0 | Create wireframes of the website | High priority | 4 hours | Matthew & Oli
finished | 1 | Write HTML and CSS of booking process | High priority | 2 hours | Matthew, Percy & Oli
finished | 2 | Write HTML and CSS of login and sign up system | High priority | 2 hours | Matthew & Oli
finished | 3 | Code server file to load current pages | High priority | 5 minutes | Allegra
finished | 4 | Create users database | High priority | 1 hour | Percy
finished | 5 | Create rooms database | High priority | 1 hour | Percy
finished | 6 | Create bookings database | High priority | 1 hour | Percy
finished | 7 | Write HTML and CCS of pages that create bookings | Medium priority | 30 minutes | Matthew and Oli
finished | 8 | Load bookings filtered by user from database and add them to page that manages a user's bookings | Medium priority | 40 minutes | Allegra
finished | 9 | Creating cancelling bookings system | Medium priority | 20 minutes | Allegra & Jon
finished | 10 | Write HTML and CSS of booking requests page | Medium priority | 20 minutes | Matthew & Oli
finished | 11 | Load bookings by request status from database | Medium priority | 30 minutes | Allegra & Percy
finished | 12 | Integrate system to approve or deny booking | Medium priority | 1 hour | Allegra & Percy
finished | 13 | Write HTML and CSS of admin page containing all confirmed user bookings | Medium priority | 1 hour | Matthew & Oli
partially finished | 14 | Code admin cancellation and edit of booking | Medium priority | 1 hour | Allegra & Percy
finished | 15 | Code server file to save and retreive users' account information from database | High priority | 1 hour and a half | Laura
finished | 16 | Code server file to save and retrieve room availability from database | High priority | 40 minutes | Jon & Percy
finished | 17 | Code javascript of booking process | High priority | 3 hours | Jon & Percy
finished | 18 | Code javascript of login and sign up system | High priority | 2 hours | Jon & Laura
finished | 19 | Create outlook calendar for every room | Medium priority | 20 minutes | Laura
finished | 20 | Code javascript of page showing booking statistics to admin | Low Priority | 4 hours | Allegra
finished | 21 | Create system that allows users to edit their bookings (+ admin confirmation) | Low Priority | 2 hours | Allegra
finished | 22 | Create diagrams showing room's availability | Minimum priority | 4 hours | Matthew
finished | 23 | Create system to allow users to book a specific desk or work station | Minimum priority | 4 hours | Percy
partially finished | 24 | Create HTML and CSS of page showing booking statistics to admin | Low Priority | 1 hour | Allegra & Oli
in process | 25 | Add security measures system | Low priority | 6+ hours | Laura
in process | 26 | Obtain pictures of the rooms for site usage | Minimum priority | 2 hours | Oli
in process | 27 | Insert images of the rooms | Minimum priority | 10 minutes | Oli
finished | 28 | Write HTML and CSS of calendar page | Medium priority | 1 hour | Allegra
partially finished | 29 | Creating confirmation and notification emails system | Low priority | 2 hours | Allegra & Jon
in process | 30 | Connect the calendar to the booking system | Medium priority | 3 hours | Laura
in process | 31 | Integrate calendar into calendar page | Medium priority | 30 minutes | Laura
in process | 32 | Refine and test | Medium Priority | Until end of sprint | All
not started | 33 | Continue implementing security measures | Low Priority | 6+ hours | Laura
not started | 34 | Create guidance document | Minimum priority | 1.5 hours | Matthew